RISK MANAGEMENT

The trustees are aware of the Charities Commission Guidance on risk management issued in July 2007.  They know their responsibility to identify existing risks and new risks as circumstances change, to mitigate risks where possible and to rate risks according to the likelihood of occurrence and the potential severity of the impact should they occur.

The trustees have identified the following existing risks.

| Risk | Mitigation | Likelihood | Impact |
| --- | --- | --- | --- |
| Governance and management |  |  |  |
| Failure by trustees | Clear understanding of roles and responsibilities, regular meetings, realistic targets. | Low | High |
|  | Trustees have relevant skills and experience | Low | High |
| Loss of records | All records kept on computer and on paper | Very low | High |
| Operational risks |  |  |  |
| Failure of communication with HRRH | Explore reasons at next visit | Moderate | Very high |
| Trainees do not attend sessions | Liase with Hoima team. Careful preparation | Low | Very high |
| Training does not improve clinical practice | Planned monitoring, review training methods if need be. | Moderate | Very high |
| HHFT pulls out | Regular review meetings | Very low | Very high |
| HRRH pulls out | Regular review meetings | Very low | Very high |
| Not enough volunteers | Plan well in advance. Subsidise costs as far as possible. | Moderate | Very high |
| No team leader | Plan well in advance. | High | Very high |
| Financial risks |  |  |  |
| Failure of fundraising | Realistic targets | Low | Moderate |
| Budgeting and cash flow | Careful plans for each visit | Low | Moderate |
| Misappropriation of funds | No plans to transfer money to HRRH | None |  |
|  | Team leader to account for cash spent in Uganda | Low | Low |
|  | Robust accounting and reporting procedures | Low | High |
| Uganda currency fluctuations | Could be a risk or a benefit | Low | Low |
| Environmental and external |  |  |  |
| Harm to volunteers | Guidance and disclaimer written. Group insurance. | Low | Medium |
|  | Supply of ARV’s in case of needle stick injury | Low | Low |
| Law and regulation compliance |  |  |  |
| Changes to law and regulation | Trustees to maintain awareness of change in UK and Uganda | Low | Low |